| Actions / Campaigns |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Activity symbol | Time | Activity | country | envisaged results and products | factual results and products: Links | factual results and + products: comments | Dissemination |

| M1 | Sep 16 | Project meeting: | DE FI PL | Precise plan of project management | Precise plan of project management www.g20hanza.pl http://www.g20hanza.pl/autoinstalator/joomla1/images/gazetka/15_16/r27_15.pdf (PDF) | Preparatory meeting: 7.12-11.12.2015 Interview of a Polish student with project coordinators from Finland and Germany in a school magazine. The interview concerned the school life and customs connected with Christmas in the countries of project partners. | School websites. magazines |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Partner schools from Poland and Finland visit the school in Germany. |  | knowledge of evaluation tools | knowledge of evaluation tools |  | Local media |
|  |  | Partners: |  |  |  |  |  |
|  |  | - get to know teacher staff |  |  |  |  |  |
|  |  | - arrange details connected with project realization: |  |  |  |  |  |
|  |  | - deciding on task division between partners, |  |  |  |  |  |
|  |  | - arranging final deadlines, |  |  |  |  |  |
|  |  | - evaluation tools, |  |  |  |  |  |
|  |  | - dissemination of information and products of the project, |  |  |  |  |  |
|  |  | - organizing project management on The internet - Schulcommsy |  |  |  |  |  |
| A1 | Sep 16 | 1. Research of the present situation - beginning questionnaire, (the same questions on eating habits for each school)/Online | DE FI PL | 1. the report with the analysis of the research with conclusions | Finland: https://peda.net/hankkeet/food/questionnaires/bq2/bq Poland: https://peda.net/hankkeet/food/questionnaires/bq2/bqp Germany: https://peda.net/hankkeet/food/questionnaires/bq2/bqg2 |  | Project website |
| A2. | Sep 16 | 1. Starting the student portfolio – online version (TwinSPace) | DE PL FI | 1. On – line questionnaire | https://peda.net/hankkeet/food/blog | Polish and Finland pupils started their portfolio in a form of a blog | Project website |
|  |  |  |  |  | https://peda.net/hankkeet/food/blog/gsb/anne-merle-schulz |  |  |
| A3 | Oct 16 | Activities connected with nutritional pyramid (passing information, learning): | DE | a) Comparison of the beginning questionnaire results with the nutritional pyramid (food circle). published on the www. | https://peda.net/hankkeet/food/sif2/food-pyramid | Students working on nutritional pyramid before visiting Finland (2 photos) | a)b) Project website |
|  |  | a) comparison of the beginning questionnaire results with the nutritional pyramid (food circle). | FI |  | https://peda.net/hankkeet/food/questionnaires/bq2/bqg2/bq:summary | Questionnaire and results | Erasmus corners |
|  |  | b) Workshops on nutritional pyramid. | PL | b) Results of students’ work on nutricial pyramid: pictures, posters, mind maps, etc. | https://peda.net/hankkeet/food/sif2/food-pyramid |  |  |
| A4 | Oct/Nov 16 | a)Students learn food and cooking vocabulary in English language, | DE | a)Students know the names of food products and vocabulary connected with preparation of food, | https://peda.net/hankkeet/food/rav | traditional foods from each participating country | Project website |
|  |  | b) students prepare a phrasebook /picture dictionary with food vocabulary. | FI |  | https://peda.net/hankkeet/food/rav/vocabulary | colletion of useful words | Erasmus corners |
|  |  |  | PL | b)phrasebook /picture dictionary with food vocabulary. | https://peda.net/hankkeet/food/piawie/products https://peda.net/hankkeet/food/piawie/activities | drafts of food connected to english vocabulary During some workshops with the language class Polish |  |
| C1 | Nov 16 | Students from Germany and Poland visit Finnish school (Kotka). | DE | 1. Conclusions from the discussion. | https://peda.net/hankkeet/food/sif2?session-tdid=3b54a852-6695-4528-8ba9-d8efbf23f46f | students discuss their eating habits and find differences | newspaper, see A5 |
|  |  |  |  |  | http://www.ernestinenschule.verwaltungsportal.eu/seite/367048/Kotka%202016.html | cooking session (link to new HP) |  |
|  |  | 1. Discussion on different eating habits in each country between students from each country. (based on the results of work so far) | FI | 2. Students know how to prepare food in a healthy way. | http://www.ernestinenschule.de/index.php?option=com_content&view=article&id=563&Itemid=269 https://peda.net/hankkeet/food/activities/conh | cooking session (link to old HP) students discuss their eating habits and find differences |  |
|  |  | 2. The presentation by a professional cook/teacher on healthy food preparation | PL | 3. Students know vocabulary to be used while cooking. | https://peda.net/hankkeet/food/rav/vocabulary |  |  |
|  |  | 3. English language activities run by international team of teachers (exchange of good practice) |  | 4. The cookery book with prepared meals |  |  |  |
|  |  | 4. Preparing Masterchef competition in international groups (deciding on the menu, buying products) |  | 3-5.The meals – photo story of the meal eaten together, written recipes used by students. | https://peda.net/hankkeet/food/blog/gsb/anders%27s-blog | extract from students blog on masterchef competition |  |
|  |  |  |  |  | https://peda.net/hankkeet/food/sif2/mc | documentation of competition in peda.net |  |
|  |  | 5. Masterchef (Finland) – cooking a healthy meal in international teams. |  |  | https://peda.net/hankkeet/food/sif2/mc/fct | International teams |  |
|  |  | 6. Teachers are presented the idea of the “cooking curriculum” in Finland. (presentation by educational authorities in Finland) (exchange of good practice) |  | 6.The teachers obsereve teaching cooking is a separate subject. |  |  |  |
| A5 | Dec 16/Jan 17/Feb 17 | Presentation to fellow students, teachers and parents on the trip to Finland. | DE PL FI | - Multimedia presentation | https://peda.net/hankkeet/food/sif2 Finland 2017 Pictures https://photos.google.com/share/AF1QipO-35Tux50fA8KNFelP5FsVOvSq_yFQWzZLxE8EozF9K8FhOBEiwBZ-O7laOa3wFw?key=WERSWWFKMnptbXV4VTdEVXRFTDZzeWl2Szg4ZlZ3 | Video presentation on the week in Finland Prezi-Presentation on food additves Polish students presented the results to other students in project lessons and on a leaflet to parents. The photo gallery presented on school halls and on school website. | Project website |
|  |  |  |  | - Fhoto exhibition (in every school) from visit to Finland | https://peda.net/hankkeet/food/sif2/pictures |  | School website |
|  |  |  |  | -All other students and teacher are informed about the project activities in Finland and benefit from them. | https://peda.net/hankkeet/food/sif2/presentation |  | Erasmus corners |
| A6 | Dec 16/Jan 17/Feb 17 | A campaign in the German school to improve/ change the way of feeding students in the school canteen. | DE | A6. Germany - official letter to educational authorities concerning feeding students in schools. | https://peda.net/hankkeet/food/project-partners/kes |  | Open letter |
| A7 | Dec 16/Jan 17/Feb 17 | Introducing healthy eating habits among students - healthy days campaign (vegetable Monday, fruit Friday, lunch box day, ideal school shop/canteen offer (stalls) in cooperation with students’ council.) | PL | A7 a photo and film record of a campaign passed to partners; | http://www.g20hanza.pl/autoinstalator/joomla1/index.php/2014-03-16-19-25-24/1222-dzien-warzyw-i-owocow-25-04-2018 https://photos.google.com/share/AF1QipM9FC14JJxZVnaO3W5m6HZUWa2p1dYnmaFc__zlpE8NcNGFUURQ1aCsDHn7lti7-w?key=RUNoZW40RWZUdWh1WGlzTTJESUJMdDgydjFrNWdn | Healthy food days: - Polish student council regularly organised healthy days: 25.04.2018r vegetable and fruit day. During school breaks students served healthy snacks. like apples, pears, tangerines, cucumbers and peppers. | School magazine Bucher |
| A8 | Dec 16/Jan 17/Feb 17 | Preteach vocabulary connected with food, what’s included in food products (chemical preservatives, regulators, colorants, glutamates, etc). | DE | Presentations | https://peda.net/hankkeet/food/rav/vocabulary | English lessons for all the classes - Finland, Poland |  |
| A9. | Dec 16/Jan 17/Feb 17 | Learning about and presentation on table manners. | DE FI PL | Presentation on table manners, recorded |  | Students from all partner schools prepared short presentation on table manners in their countries. | Project website |
|  |  |  |  |  |  |  | School website |
| A10 | Jan 17/Feb 17/Mar 17 | 1. Preparing a show by a school cabaret connected with eating and table manners. | PL | 1. A show plan/scenario | file:///C:/Users/katarzyna/Downloads/r35_16%20(1).pdf | Polish students prepared a drama o table manners through centuries. | Project website |
|  |  | 2. Presenting the show for local primary school students during school open day and open lessons |  | 2. Recorded school cabaret show. |  | PL Show ‚table manners through centuries’ presented during School Open Day (21.03) | School website |
|  |  |  |  |  |  |  | The show presented for local primary school students during school open day and open lessons |
| C2 | Mar 2017 | Students from Germany and Finland visit Polish school (Gdansk) | DE | 1.Students know the content of food and its influence on our body. | https://peda.net/hankkeet/food/msip2#nav | 1.Lecture on food additives – Medical University of Gdansk 2.Presentations of partner schools ‘Table manners’ | newspaper, see A11 |
|  |  | 1. FOOD Lectures and international WORKSHOPs - | FI | 2.Multimedia presentation. |  |  |  |
|  |  | ‘ Do you know what you eat?’ studying food additives in products: preservatives, regulators, colorants, glutamates, etc, grouping them, calculating calories. | PL | 3.They know how and where to shop for healthy food. |  |  |  |
|  |  | (lectures at The University of Gdańsk) |  | 4. pictures of a healthy snack – burger. |  |  |  |
|  |  | 2. Table manners and lying the table – presentations |  | 5. Photo-reports, interview. | https://peda.net/hankkeet/food/msip2/table-manners |  |  |
|  |  | 3. Shopping for healthy food – game at a supermarket and at healthy food bazar. |  | 6.Photo and art exhibition. | https://peda.net/hankkeet/food/msip2/pictures/healty-breakfast | Pupils from Finland, Germany and Poland prepare a healthy snack. During the Polish week (19-25.03.217) there was a cooking workshop. |  |
|  |  | 4. Students prepare a healthy burger. |  |  |  |  |  |
|  |  | 5. Art workshops: |  |  |  |  |  |
|  |  | - Student make their works of art (e.g. an image of their favourite meal, fruit and vegetable images |  |  | https://peda.net/hankkeet/food/msip2/art-workshop |  |  |
| A12. | Apr 17 | Healthy resolutions challenge in each country (the students make decision what they can do without or what they can do extra, for example – no chocolate, coke, burger for three weeks/ or carrots every day) |  | Challenge diaries in a blogs: | https://peda.net/hankkeet/food/blog/fsb | Healthy resolutions challenge in each country - a week before Easter (24.04 – 30.04 2017). The students made decision what they could do without or what they could do extra, wrote about their challenge on the blog and observed the challenges of their foreign friends on the blog- for example Finland | Campaigne with students organisation |
| C3 | 08. May | Students from Poland and Finland visit German school (Lübeck) | DE | 1. Students and teachers from all partner schools know about different ways of food production. They are more conscious while buying certain food products. | https://peda.net/hankkeet/food/msip223/pofrd |  |  |
|  | 2017 | 1. Visiting three kinds of food production places. Students and teachers from all partner schools learn about different ways of food production. | FI | 2. a) Teachers from Poland and Finland know an innovative method - a role play with the use of ICT. |  |  |  |
|  |  | a) Brüggen: one of the fastest-growing and leading cereal manufacturers in the world (meeting one of the owners, question session with one of the owners) | PL | b) method description. |  |  |  |
|  |  | b) Ersaco: part of an international Food Company without(!) an ecolgical image |  |  |  |  |  |
|  |  | c) Ringstedtenhof: An Ecological Farm with a bioshop and educational training for students, food workshops |  |  | https://peda.net/hankkeet/food/msip2s/pictures/biofarm | Biofarm |  |
|  |  | 2. Students’ roleplay “setting up a company - we are food manufacturers” |  |  |  |  |  |
| A14 | May/June 2016 | Presentation to fellow students, teachers and parents on the trip to Germany | PL,FI, DE | Presentations/photos | https://peda.net/hankkeet/food/msig13 |  |  |
| M 2 | Sep 17 | Teachers (only) have a follow-up meeting in Finland to evaluate the project and plan the second year of the project | DE,PL, FI | Plans ,Evaluation analysis |  | The meeting was moved to August 2018 |  |
| A16 | Sept/Oct 2017 |  |  | 1. Studying the problem of eating disorders | https://peda.net/hankkeet/food/msip223/lafrd/diabetes |  |  |
| C4 | October 2017 | Students from Germany and Finland visit Polish school (Gdansk) | DE | 2. Students know the etiology of the eating disorders and can recognize the signs of disorders. |  | - a location-based game: monuments and restaurants (find a healthy restaurant rally - Working on the map of the restaurant and blog |  |
|  |  | 1. (compulsive eating/ bulimia/ anorexia/ type 2 diabetes/ obesity/ food allergies and intolerances). and creating a play or a cartoon on this topic - theoretical background – workshops conducted by professional institutions handling disorder prevention. (Boys and girls handle the problems separately. Separate workshops.) | FI | - Leaflet with the description of disorders and their symptoms. | https://peda.net/hankkeet/food/msip223/lafrd | Students worked in 3 international groups making a cartoon on food related diseases, Leaflets and drama. 3. Product presentation for parents. |  |
|  |  | 3. Teachers from Finland and Germany are presented the work of school psychologist and social worker in the Polish school. (hopefully the social worker from Finland comes to visit Poland in November 2017). 4. Teachers from Finland and Germany learn how students are supported by a team of school psychologist and social worker in the Polish school. |  |  | https://photos.google.com/share/AF1QipM7sPsPK8txQYAZeviJ9wgBs75XGEqHSVYtgS_brysz08IXvDYf6h5oz-1R8CpZTA?key=VzdTb2tmTWJ2cTV1N0o1cWNOVXM5ckowTXg5SWFR |  |  |
|  |  |  |  | . |  |  |  |
| A 17 | a)Nov 17/Dec 17 | 1. Students study the problem of wasting food at student’ homes/ in factories/restaurants/ shops/ (each country) and learn to prevent it: | DE | Students are aware of the problem of wasting food and lean to prevent it. | https://peda.net/hankkeet/food/msig13/food-waste | - Studying the problem of wasting food at student’ homes/ in factories/restaurants/ shops/ (each country) and learn to prevent it |  |
|  |  | b) Students measure the amount of wasted food in their households (in certain period of time) | PL | b) Visuals showing wasted food (graphs, images) | https://peda.net/hankkeet/food/msig13/food-waste |  |  |
| C5 | Mar 18 | Students from Poland and Finland visit German school (Lübeck) | PL,FI, DE |  | https://peda.net/hankkeet/food/msig13 |  |  |
|  |  | a) Visiting organizations collecting expired date food and giving it to the poor, e.g. Lubeca Tafel (in Germany) |  |  |  |  |  |
|  |  | b) Learning about FREEGANISM movement. |  |  | https://peda.net/hankkeet/food/msig13/food-waste/freeganism |  |  |
| A18 | March/April 2018 | Research on eating habits of people with different food philosophy. (Vegetarian, Vegan, Kosher, with meat without pork) – questionnaires and interviews. | DE, PL, FI | questionnaires and interviews written down/ recorded | https://peda.net/hankkeet/food/msif11/fpp | Pupils do it-(Vegetarian, Vegan, Kosher, with meat without pork) – questionnaires and interviews | interpretation on the website |
| A19 | May 2018 | Polish students organize restaurant rally to search for the examples of different food philosophy. | PL | The plan of a restaurant rally and the map with healthy and unhealthy food restaurants. | http://www.g20hanza.pl/autoinstalator/joomla1/index.php/2014-03-16-19-25-24/1222-dzien-warzyw-i-owocow-25-04-2018 |  | Website |
| A20 | May 2018 | Preparing the debate or discussion ‘ I am what I eat’ | FI, DE,PL | The debate roles or discussion points written down | https://peda.net/hankkeet/food/msif11/fpp | . Discussions. |  |
| C6. | May 18 | Students from Poland and Germany visit Finnish school (Kotka) | DE,FI, PL | Multimedia presentations, pictures, video recordings of the interviews. | https://peda.net/hankkeet/food/msif11/fpp |  | newspapers |
|  |  | Presentations and Comparison of eating habits and opinions of people with different food philosophy. (Vegetarian, Vegan, Kosher, with meat, without pork). Interviews with Finnish main kitchen workers – to learn about the variation of meals served to students. (Vegetarian, Vegan, Kosher, with meat, without pork) - presentation |  |  | https://peda.net/hankkeet/food/msif11/photos |  |  |
|  |  | DEBATE: “I am what I eat” all schools participation. |  |  |  |  |  |
| A22 | Jun 18 | Final evaluation questionnaire in each partner country | FI, PL,DE | Evaluation questionnaire with the results. | https://peda.net/hankkeet/food/msif11/photos/mkik |  |  |
|  |  |  |  | Discussion about Curricula at schools |  |  |  |
| A23 | Jul 18 | Working out the conclusions from evaluation, | DE, PL,FI | Multimedia Presentation of Evaluation conclusions and summary of the project presentation Discussion about Curricula at schools | https://peda.net/hankkeet/food/msif11 |  |  |
| A24 | Jul 18 | dissemination of project materials the materials. | FI,DE,PL | All project products are disseminated |  |  | e-twinning, final report in the newspapers |
|  |  |  |  | Info on project www e-twinning and other portals/ leaflets, school magazines | https://peda.net/hankkeet/food/msif11#nav |  | websites |
| A25 | Aug 18 | Working on final report, budget. | DE,FI,PL | final report. |  |  |  |